## Product Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
2 | Product Backlog item 2 | 2.1 | As an Admin, I want to login to my admin account so that I can access my admin profile. | Jared |  |  | x
|  | 2.2 | Add front-end functionality | Jared |  |  | x
|  | 2.3 | Add back-end functionality | Jared |  |  | x
3 | Product Backlog item 3 | 3.1 | As an Admin, I want to view all current users, so that I can see all user information. | Aili |  |  | x
|  | 3.2 | Add front-end functionality | Aili |  |  | x
|  | 3.3 | Add back-end functionality | Aili |  |  | x
4 | Product Backlog item 4 | 4.1 | As an Admin, I want to modify user accounts, so that I can edit user information. | Aili |  |  | x
|  | 4.2 | Add front-end functionality | Aili |  |  | x
|  | 4.3 | Add back-end functionality | Aili |  |  | x
5 | Product Backlog item 5 | 5.1 | As an Admin, I want to modify users, so that I can suspend/unsuspend users from their account. | Aili |  |  | x
|  | 5.2 | Add front-end functionality | Aili |  |  | x
|  | 5.3 | Add back-end functionality | Aili |  |  | x
6 | Product Backlog item 6 | 6.1 | As an Admin, I want to add new books, so that new items can be sold. | Alexander |  |  | x
|  | 6.2 | Add front-end functionality | Alexander |  |  | x
|  | 6.3 | Add back-end functionality | Alexander |  |  | x
7 | Product Backlog item 7 | 7.1 | As an Admin, I want to edit books, so that I can update the correct data. | Alexander |  |  | x
|  | 7.2 | Add front-end functionality | Alexander |  |  | x
|  | 7.3 | Add back-end functionality | Alexander |  |  | x
22 | Product Backlog item 22 | 22.1 | As a business user, I want to be able to login to my business account so that I can access my business profile | Jared |  |  | x
|  | 22.2 | Add front-end functionality | Jared |  |  | x
|  | 22.3 | Add back-end functionality | Jared |  |  | x
25 | Product Backlog item 25 | 25.1 | As a business user, I want to be able to see all previous transactions, so I know how often transactions are happening. | Shannon |  |  | x
|  | 25.2 | Add front-end functionality | Shannon |  |  | x
|  | 25.3 | Add back-end functionality | Shannon |  |  | x
29 | Product Backlog item 29 | 29.1 | As a business user, I want to be able to edit the books I am managing, so I can fix mistakes when originally created the book page. | Shannon |  |  | x
|  | 29.2 | Add front-end functionality | Shannon |  |  | x
|  | 29.3 | Add back-end functionality | Shannon |  |  | x
31 | Product Backlog item 31 | 31.1 | As a customer, I want to be able to register a user account so that I can buy, share or sell used books. | Carl |  |  | x
|  | 31.2 | Add front-end functionality | Carl |  |  | x
|  | 31.3 | Add back-end functionality | Carl |  |  | x
32 | Product Backlog item 32 | 32.1 | As a customer, I want to be able to search for books so that I can view information about the book. | Carl |  |  | x
|  | 32.2 | Add front-end functionality | Carl |  |  | x
|  | 32.3 | Add back-end functionality | Carl |  |  | x
42 | Product Backlog item 42 | 42.1 | As a Customer, I want to be able to view my transaction history, so that I can see all my recently bought books | Carl |  |  | x
|  | 42.2 | Add front-end functionality | Carl |  |  | x
|  | 42.3 | Add back-end functionality | Carl |  |  | x
45 | Product Backlog item 45 | 45.1 | As a Customer, I want to create an account so I can peruse and purchase items | Jared |  |  | x
|  | 45.2 | Add front-end functionality | Jared |  |  | x
|  | 45.3 | Add back-end functionality | Jared |  |  | x
51 | Product Backlog item 51 | 51.1 | As a customer, I want to view the details of the book I am thinking of buying, so I can be more informed on my decision. | Shannon |  |  | x
|  | 51.2 | Add front-end functionality | Shannon |  |  | x
|  | 51.3 | Add back-end functionality | Shannon |  |  | x

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Product Backlog item 2 | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Product Backlog item 3 | #N/A | #N/A | #N/A | #N/A | #N/A
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Product Backlog item 5 | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Product Backlog item 6 | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Product Backlog item 7 | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Product Backlog item 22 | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Product Backlog item 25 | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A